## Sheet1
Project Name |  | QTRecognition
Project ID |  | QTR
Build/Release Version
Defect ID | Module | Build Version | Reported by | Reported Date | Defect Description | Steps to Reproduce | Severity | Status
D01 | Verification |  | Abdul Azeem A H | 2021-12-03 | When user try to Login with invalid credentials Login page is Redirected to a blank page | 1. Enter invalid username 2. Enter invalid password 3. click on login Button | Major | New
D02 | Verification |  | Abdul Azeem A H | 2021-12-03 | UserName field is not a CaseSensitive if a user try to enter valid username in Mixed case it doesn't check for CaseSensitive of character.Even though there is case mismatch it allows to Login | 1) Enter the valid Username with mixed case 2) Enter the valid Password 3) Click the Login Button eg)PRANESH.dixit@QUALITESTgroup.com | Major | New
D03 | Verification |  | Abdul Azeem A H | 2021-12-03 | Password field is not a CaseSensitive if a user try to enter Password in Mixed case it doesn't check for CaseSensitive of character.Even though there is case mismatch it allows to Login | 1)Enter the valid UserName with mixed case 2)Enter the valid Password with mixed case 3) Click the Login Button eg)p@ssW0RD | Major | New
D04 | Verification |  | Abdul Azeem A H | 2021-12-03 | Login Session was not closed while back button on browser is clicked | 1)Login QTRecognition with valid credentials 2)click the back Button in browser 3)Clear the input fields 4)Click the forward button on any browser | Critical | New
D05 | Verification |  | Abdul Azeem A H | 2021-12-03 | Color of Myheading division is #fdcc16. It doesn't match the Qualitest approved primary colors. it doesn't match the Qualitest approved primary colors. | 1) Launch any browser 2) Enter valid Url of QTRecognition 3) Right Click and select inspect option from pop-up menu 4) Select an element to inspect it Button 5) Select Myheading div to verify color | Minor | New
D06 | Verification |  | Abdul Azeem A H | 2021-12-03 | Color of container class division should be #FECC160-Gold or #2A2559-Navy or #939598-White | 1) Launch any browser 2) Enter valid Url of QTRecognition 3) Right Click and select inspect option from pop-up menu 4) Select an element to inspect it Button 5) Select Division Container to verify color | Minor | New
D07 | Activity Page |  | Abdul Azeem A H | 2021-12-03 | Image is not displayed in the left-handside of the screen | 1)Login QTRecognition with valid credentials 2) Check the Image is Displayed at the Left-handside of the screen | Minor | New
D08 | Activity Page |  | Abdul Azeem A H | 2021-12-03 | Activities are displayed in Recent Activities with Wrong Date | 1)Login QTRecognition with valid credentials 2)Check the Activities | Major | New
D09 | Activity Page |  | Abdul Azeem A H | 2021-12-03 | Only Recent five kudos sent by me is Displayed on Recent Activities with wrong date | 1) Login QTRecognition with valid credentials 2) Click Kudos for me HyperLink dispalyed in UserOption 3) Check the Recent Activities will updated with Kudos sent to me | Major | New
D10 | Activity Page |  | Abdul Azeem A H | 2021-12-03 | Error Occured: Failed to load resource: the server responded with a status of 403 ()- a076d05399.js:1 | 1) Login QTRecogition with valid credentials 2) Right click on the Webpage on browser and Select Inspect 3) check console window to check any error occured | Major | New
D11 | Activity Page |  | Abdul Azeem A H | 2021-12-03 | Scroll bar in the Recent Activities is working as expected | 1) LoginQTRecognition with valid credentials 2) Scroll the Recent Activities using scroll bar | Minor | New